## FRP
Quality Control Record
Sarah Solutions Centre - Roofing
Section 1 - General Details
Package: |  | FRP |  | No: | 1
Worklot-Sublot: |  | Concrete Placement |  | File Location: | QA-FRP
Location/Building: |  | Raft Slab
Discipline: |  | Concretor
Contractor: |  | Ngurra Civil & Construction
Number of Stages: |  | N/A
Design Documentation - No. & Revision
Specification: |  | N/A
Drawing: |  | Architectural: Sarah - Markup Sketch NB
Structural: 9999-MP01[A]
Section 2 - Technical Submissions & Approvals
Description |  |  | Verification | Status | Reference
FRP - ITP & Checklist for Approval |  |  | Document / F-96 | Closed | T-123 ITP - Concrete
Concrete Mix Design Approval |  |  | Certificate / Sign Off | Closed | FRP - Concrete Mix Design Approval - 1
Records of Engineer's Inspections |  |  | Report | Closed | N/A - nil items to Rectify
Curing Methods |  |  | Certificate / Sign Off | Closed | XDS tech Data Sheet
Concrete Curing - ITP & Checklist for Approval |  |  | Document / F-96 | Closed | T-123 ITP - Concrete
Formwork Engineering Design |  |  | Certificate / Sign Off | Closed | Formwork Certificate
Confirmation of Floor Finish & Falls |  |  | Visual Check | Closed | Photographs
Approval of Concrete Supplier |  |  | Sign Off | Closed | Mix Design
Reinfrocement Supplier Certification |  |  | ACRS Certificate | Closed | ACRS Certificate - Infrabuild
Section 3 - Contractor QA
Description |  |  | Verification | Status | Reference
FRP - Signed Subcontractor ITP |  |  | Document | Open
Concrete Dockets |  |  | Dockets | Closed | Concrete Docket - Hanson
Reinforcement Delivery Dockets |  |  | Dockets | Open
Reinforcement Material Testing |  |  | Mill Certificates | Open
Concrete Test Results - 7 Days |  |  | NATA Test Report | Closed | N/A
Concrete Test Results - 28 Days |  |  | NATA Test Report | Closed | N/A
Concrete Shrinkage Test Results - 56 Days |  |  | NATA Test Report | Closed | N/A
Termite Treatment |  |  | Check | Closed | N/A
Compliance of Concrete Test Results with Specification |  |  | Check | Open
Concrete Curing - Signed ITP |  |  | Document | Open
As-Built Documentation |  |  | Survey Report | Open | As per 9999-MP01[A]
Section 4 - Sarah QA
Description |  |  | Verification | Status | Reference
Concrete Pour Checklist |  |  | F-67 | Closed | Pre-pour Checklist
Pour Diagrams / Lot Plans |  |  | Document | Closed | N/A
Completion of Concrete Pour Register |  |  | R-47 | Closed | Refer R-47
Evidence of Completed Corrective Actions |  |  | Photos | Closed | Refer R-24
QA Photos |  |  | Photos | Closed | See Photographs
Council Notification of Footing Strip, Cut & Fills |  |  | Document | Closed | Regulation 74 Notification
Non Conformances
No. | Comment |  |  | Status | Date Closed
1
2
3
4
5
Package Status
Open |  | 6
Closed |  | 20
Total Complete (%) |  | 76.92%
Note on A21: Concrete mixes: Submit details, for each grade and type of concrete including any proposed use of special-purpose cement types.
Note on A22: Reinforcement Inspections: - Cores and embedments fixed in place. - Reinforcement fixed in place, with formwork completed. Concrete In-Situ On-Site Inspections: - Base or subgrade before covering. - Completed formwork and reinforcement, tendons, cores, fixings and embedded items fixed in place before placing concrete. Concrete Finishes On-Site Inspections: - Completed formwork before placing concrete. - Evaluation of the off-form finishes. - Evaluation of surface finish.
Note on A23: Submit details of any proposed curing compounds, including the following: - Certified test results for water retention to AS 3799 Appendix B for liquid membrane-forming compounds. - Evidence of compatibility with concrete, and with applied finishes including toppings and render, if any, including methods of obtaining the required adhesion. - For visually important surfaces, evidence that an acceptable final surface colour will be obtained.
Note on A25: Certification Formwork design certification: For other than permanent composite form systems, submit certification by a professional engineer experienced in formwork design verifying conformance of the design. Formwork execution certification: Submit certification by a professional engineer experienced in formwork design and construction, verifying conformance of the completed formwork, including the suitability of the formwork for the documented surface finish class. Formwork calculations: Submit calculations by a professional engineer experienced in formwork design to show that allowable concrete stresses will not be exceeded and formwork capability will be maintained if the following is proposed: - Formwork procedures or loadings that differ from those documented. - Props above a floor that do not coincide with the props below. - Undocumented formwork shoring or stripping procedures. - Loadings from stacked materials.
Note on A27: Pre-mixed supply: Submit names and contact details of proposed pre-mixed concrete suppliers and alternative source of supply in the event of breakdown of pre-mixed or site mixed supply.
Note on A28: Certification of Reinfocement Supplier to AS/NZS 4671 by External Third Party - ACRS Certificate
Note on A35: Reinforcement strength and ductility: Submit type-test reports as evidence of conformance to AS 3600 Table 3.2.1 for each reinforcement type.
Note on A36: General Test authority: Concrete supplier or an Accredited Testing Laboratory. Reports and records of test results: To the relevant parts of the AS 1012 series. Keep results on site. Assessment process of test results Standard: To AS 1379. Method of assessment: Project assessment Sampling Method of sampling: AS 1012.1. Sampling locations: To AS 1012.1 and the following: - Slump tests: On site, at the point of discharge from the agitator. - Compressive strength tests: Spread the site sampling evenly throughout the pour. Frequency of sampling: To AS 1379 Sections 5 and 6 and the following: - Slump tests: Take at least one sample from each batch. - Compressive strength tests: (REFER SPECIFICATION) for further details Making and curing of specimens General: To AS 1012.8.1 and AS 1012.8.2. Specimens for compressive strength tests: Make and cure at least two specimens from the sample of each grade. Specimen size: - Aggregate size ≤ 20 mm: Nominally 200 x 100 mm diameter. - Aggregate size > 20 mm: Nominally 300 x 150 mm diameter. Test methods General: To the relevant parts of the AS 1012 series. Acceptance criteria: - General: As documented in the General Drawing Notes. - Drying shrinkage at 56 days: To AS 1012.8.4 and AS 1012.13.
Note on A37: General Test authority: Concrete supplier or an Accredited Testing Laboratory. Reports and records of test results: To the relevant parts of the AS 1012 series. Keep results on site. Assessment process of test results Standard: To AS 1379. Method of assessment: Project assessment Sampling Method of sampling: AS 1012.1. Sampling locations: To AS 1012.1 and the following: - Slump tests: On site, at the point of discharge from the agitator. - Compressive strength tests: Spread the site sampling evenly throughout the pour. Frequency of sampling: To AS 1379 Sections 5 and 6 and the following: - Slump tests: Take at least one sample from each batch. - Compressive strength tests: (REFER SPECIFICATION) for further details Making and curing of specimens General: To AS 1012.8.1 and AS 1012.8.2. Specimens for compressive strength tests: Make and cure at least two specimens from the sample of each grade. Specimen size: - Aggregate size ≤ 20 mm: Nominally 200 x 100 mm diameter. - Aggregate size > 20 mm: Nominally 300 x 150 mm diameter. Test methods General: To the relevant parts of the AS 1012 series. Acceptance criteria: - General: As documented in the General Drawing Notes. - Drying shrinkage at 56 days: To AS 1012.8.4 and AS 1012.13.
Note on A38: Test methods General: To the relevant parts of the AS 1012 series. Acceptance criteria: - General: As documented in the General Drawing Notes. Drying shrinkage at 56 days: To AS 1012.8.4 and AS 1012.13.
Note on A40: Check 28 day test results to ensure design strength of concrete has been achieved.
Note on A41: Quality Checklist requires completion by Concreter for Deflecta Warranty to be valid.

## Structural Steel
Quality Control Record
Sarah Solutions Centre - Roofing
Section 1 - General Details
Package: |  | Structural Steel |  | No: | 1
Worklot-Sublot: |  | Structural Steel - Roof |  | File Location: | QA - Structural Steel
Location/Building: |  | Structural Steel - Roof
Discipline: |  | Structural Steel
Contractor: |  | Gant
Number of Stages: |  | N/A
Design Documentation - No. & Revision
Specification: |  | N/A
Drawing: |  | Architectural: Sarah - Markup Sketch NB
Structural: 9999-MP01[A]
Section 2 - Technical Submissions & Approvals
Description |  |  | Verification | Status | Reference
Submission of Subcontractor ITP for Approval |  |  | Document / F-96 | Closed | T-123 ITP - Concrete
Erection & Lifting Plans Submission |  |  | Engineer Sign Off | Closed | N/A
Approval of Surface Treatment System & Product |  |  | Document | Closed | Innovation Project 2021
Approval of Fire Treatment |  |  | Document | Closed | N/A
Touch Up Paint System Compatible w Shop Treatment |  |  | Confirmation | Closed | N/A
Records of Engineer's Inspection |  |  | Report | Open
Approval of Shop Drawings |  |  | Documents | Closed | Email: M. Kilmartin
Steel Supplier Certification |  |  | ACRS Certificate | Closed | ACRS .zip file
Section 3 - Contractor QA
Description |  |  | Verification | Status | Reference
Signed Subcontractor ITP |  |  | Document | Open
NATA Test Certificates for Steel |  |  | Mill Certificates | Closed | ACRS .zip file
Material Test Certificates for all 8.8/S bolts |  |  | Certificate | Closed | ACRS .zip file
Site Weld Inspection Results (Magnetic Particle & Ultra Sonic Testing) |  |  | Report | Closed | N/A
Welding Personnel Register & Qualifications |  |  | Document | Closed | Welding Register
Paint Coating Daily Inspection |  |  | Record | Closed | N/A
Current Calibration Certificates of Laser Levels |  |  | Certificate | Closed | Laser Certification
Section 4 - Sarah QA
Description |  |  | Verification | Status | Reference
Issues Identified by Consulants Closed Out with Records |  |  | Photos/Document | Closed | Refer R-24
Temporary Engineering Due to Staged Structural Errection |  |  | Record | Closed | Photographs
QA Photos |  |  | Photos | Closed | Photographs
Agreed Lot Plan with Subcontractor |  |  | Document | Closed | N/A
Non Conformances
No. | Comment |  |  | Status | Date Closed
1
2
3
4
5
Package Status
Open |  | 2
Closed |  | 17
Total Complete (%) |  | 89.47%
Note on A27: Certification of Reinfocement Supplier by External Third Party - ACRS Certificate

## Roof & Metal Cladding
Quality Control Record
Sarah Solutions Centre - Roofing
Section 1 - General Details
Package: |  | Roofing |  | No: | 1
Worklot-Sublot: |  | Roofing - Genral Area |  | File Location: | QA - Roofing
Location/Building: |  | Roofing to Model
Discipline: |  | Roofing
Contractor: |  | Asurco (McMahons)
Number of Stages: |  | N/A
Design Documentation - No. & Revision
Specification: |  | N/A
Drawing: |  | Architectural: Sarah - Markup Sketch NB
Structural: 9999-MP01[A]
Section 2 - Technical Submissions & Approvals
Description |  |  | Verification | Status | Reference
Submission of Subcontractor ITP(s) for Approval |  |  | Document / F-96 | Closed | T-123 ITP - Concrete
Approval of Roofing & Cladding Samples, incl. Fasteners |  |  | Submission | Closed | Refer Aus Standards
Approval of products for Fire Performance Properties |  |  | Submission | Closed | Refer Aus Standards
Section 3 - Contractor QA
Description |  |  | Verification | Status | Reference
Roofing - Signed Subcontractor ITP |  |  | Document | Open
Water Testing for Roof & Gutters |  |  | Certificate | Closed | N/A - As per Aus Standards
Water Tightness Warranty |  |  | Document | Closed | Refer Installation Guidelines
Section 4 - Sarah QA
Description |  |  | Verification | Status | Reference
Review Roof Design (Downpipes, Supports for Penetrations) |  |  | Check | Closed | Email: M. Kilmartin
Roof Handover Prior to Following Trades Commencing |  |  | Sign Off | Open
Issues Identified by Consulants Closed Out w Records |  |  | Photos/Document | Open | Refer R-24
Non Conformances
No. | Comment |  |  | Status | Date Closed
1
2
3
4
5
Package Status
Open |  | 3
Closed |  | 6
Total Complete (%) |  | 66.67%
Note on A22: Requirement: Submit evidence of conformance of Fire hazard, Fire Resistance & Combustibility properties for the following - - Cladding - Glazed Roofing & Skylights - Thermal Insulation / Roof Blanket - Piable Membrane
Note on A28: Via Inspection of installation by Fielders