## Defects Register
Defects Register (R-24)
Date |  | 2021-05-21 | Project Name |  | Sarah Solutions Centre - Roofing
Construction Coordinator |  | Nathan Bowden | Site Supervisor |  | Rachel Kitto
Area | No. | Defects | Date Raised | Action By | Remarks | Status | Date Complete
External
Rasied by Steve Blackmore | 1 | The location of post bases does not relate to the steelwork above. They never marked out centre lines of posts correctly and as such nothing is plumb. Additional fixings may need to be installed to make this work. Suggest changing over base plates when you cut columns down. ( meet on site to discuss solution. This would have not happened if base plates were cast into the slab as discussed early in the project. | 2021-05-21 | RK/ NB | Base Plates Changed over to 200 x 200 with 75 deg chamfer on internal, to allow for 3 bolt fixing. | In Progress
Rasied by Steve Blackmore | 2 | Red and grey posts to be swapped around when they get shortened. Suggest they need 600mm off of them | 2021-05-21 | RK/ NB | Requested from Magena when cutting posts down. 600mm reduced in height. | In Progress
Rasied by Steve Blackmore | 3 | Want to see packers under base plates as per standard installation. Suggest at least one is dry packed with grout to show what happens on site. (min 20mm packers) | 2021-05-21 | RK/ NB | Packers | In Progress
Rasied by Steve Blackmore | 4 | Once has been lowered and columns plumbed will require final clean | 2021-05-21 | RK/ NB | Has had pre clean 26/5 - will clean when in final place. | In Progress
Rasied by Steve Blackmore | 6 | Screws in compliance with Bondor Panel Installation. | 2021-06-01 | NB | Bondor panel required to be fixed on every ridge as per model with 14g Tek Screws with Cyclone Washer which complies. Although when constructing on site Colour matched screws will be affixed in lieu of standard colour. | Complete | 2021-06-02
Rasied by Steve Blackmore | 5 | Pole Flashing Compliance with Bondor Panel Installation. | 2021-06-01 | NB |  | Complete | 2021-06-02