|  |
| --- |
| ITP Details |
| **Project:** | Sarah Solutions Centre | **Activity:** | Roofing – Roof Safety System |
| **Location:** | 2 Myuna St, Regency Park | **Subcontractor:** | Mcmahons / RIS |

|  |
| --- |
| Preparation & Approval |
| **Prepared by:** | **Name: Nathan Bowden / 0437 728 628** | **Position: Construction Graduate** | **Signature:** | **Date: 11/03/21** |
| **Approved by:** | **Name: Rachel Kitto / 0403 247 330** | **Position: Site Supervisor** | **Signature:** | **Date: 11/03/21** |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Activity / Step | Acceptance Criteria | Verification Type(H / I / R / S / W) | Verification Frequency | Verification: | Records / Evidence | Comments |
| **By** | **Initial** | **Date** |
|  | Data Sheets / Physical Sample | Submit samples of products in line with the project requirement that comply with AS 1657:2018.Sample approval received from Sarah Constructions. | HP | When Samples are requested | McMahonsRIS |  |  | Report | Roof Area |
|  | Shop Drawings | Submit Shop Drawings for review and approval by Architect / Consultants. | HP | Until Approved | McMahonsRIS |  |  | Shop Drawings |  |
|  | Delivery of Materials & Check for damage | Delivered material match sample approved.Delivered material is free of water damage, corrosion and surface treatment blemishes. | HP / I | Upon delivery | McMahonsRIS |  |  | Photos | Lay down area nominated by SC. |
|  | Fixings  | As per manufacturers installation specification fixed either side of the walkway every 500 to 850mm to a support channel with neoprene seals (or similar) and AS 1657:2018 for additional fixing requirements. | I | Periodically when conducting ITP’s | McMahonsRIS |  |  | Report | Roof Area |
|  | Setout | System is set out as per approved Shop Drawings. Ensure up to date Construction Drawings are carried at all times. | HP / I | Prior to Install | McMahonsRIS |  |  | Photos | Roof Area |
|  | Installation | Installed as per Standards AS 1657:2018, Manufacturer Recommendations and location provided by approved shop drawings.Ensure all rubbish and swarf are removed from area. | W / I | During and at completion of install. | McMahonsRIS |  |  | Photos / QA sign off | Roof Area |
|  | Inspection  | Subcontractor to inspect works and provide QA documentation and sign off by manufacturer for compliance of installation. | I | Post Installation | McMahonsRIS |  |  | Photos / Certification | Roof Area |
|  | Handover | SC to handover warranties and certification in line with the Project Specification. | HP | Final Handover | McMahonsRIS |  |  | Warranty / Certification |  |

H = Hold Point I = Inspection R = Review S = Surveillance W = Witness