## QA Requirements Summary
QA Requirements Summary (T-35)
Project Title: | Sarah Solutions Centre - Roofing
Reference (e.g. Specification, Australian Standard, Manufacturer's Information etc.) | Section | Trade | Type (e.g. Sample, Inspection, Test, Prototype, Shop Drawing, etc.) | Description | Location | Verification (e.g. Hold Point, Inspection, Notification, etc.) | Evidence (e.g. test results, report, photos etc.) | Sign-off / Status
Gutters / Drainage
NCC Volume 1:2019 | Part F1 - FP.1.1 | Roofing | Requirement | Stormwater generated from average recurrence shall be disposed of in a way that avoids the likelihood of damage or nuisance to any other property | Overflow Devices / Downpipes | Inspection | Certification of Installation
| Part F1 - FP1.2 | Roofing | Requirement | Preventing stormwater from entering the building by adeuqate means of transporting surface water. | Overflow Devices / Downpipes | Inspection | Certification of Installation
| Part F1 - FP1.3 | Roofing | Requirement | Having a drainage system to remove the surface water in place. | Overflow Devices / Downpipes | Inspection | Certification of Installation
| Part F1 - FV1.1 | Roofing | Requirement | Details the requirement of Test Reports and what is to be included for acceptance. | Overflow Devices / Downpipes | Inspection | Certification of Installation / Test Reports
| Part F1 - F1.1 | Roofing | Requirement | Stormwater drainage must comply with AS/NZS 3500.3 and engineers drawings. | Overflow Devices / Downpipes | Note | Noted in Shop Drawings
Australian Standard 3500.3:2018 | Section 4.1 (Installation) | Roofing | Specification Scope | This section specifies the installation of roof drainage systems. | Guttering / Overflow Devices / Downpipes | Inspection | Certification of Installation
| Section 4.3.2 (Installation) | Roofing | Specification | Specifies the requirement of the expansions joints that are to be featured in box gutters and conforming to Standards and downpipe support systems also. | Box Gutter / Downpipes | Hold Point | Photos
| Section 4.5.1 (Installation) | Roofing | Specification | Installation and Testing is to comply with being effectively fixed and secured to satisfy the requirements of the standard, as well as maximum laps distances. | Overflow Devices / Downpipes / Box Gutters | Hold Point | Test Reports and Certification of Installation
| Section 4.5.4 (Installation) | Roofing | Specification | Requirement of the installation of the box gutter for gradients, supports, minimum outlets and lap joints | Box Gutter | Inspection | Certification of Installation
| Section 4.5.6 (Installation) | Roofing | Specification | Location, Concealement, Connections, Isolations and Support Systems required to satisfy Ausralian Standards. | Downpipes | Inspection | Certification of Installation
| Section 4.6 (Installation) | Roofing | Specification | Overflow devices for the box gutter shall comply with Section 3.7.7 (Design) for capacity and size for the box gutter. | Overflow Devices | Inspection / Hold Point | Certification of Installation
| Section 9.1 (Testing) | Roofing | Specification Scope | This section specifies the testing of roof drainage systems. | Overflow Devices / Downpipes | Testing | Test Reports
| Section 9.3.1 & 9.4.1 (Testing) | Roofing | Specification Scope | Testing for Downpipes with air and water pressure - certificates required for conformance. | Downpipes | Testing | Test Report
Australian Standard / New Zealand Standard 2179:2014 | Section 2.5.1-2.5.4 | Roofing | Specification | Specifies requirements for Zinc-Coated Steel sheet rainwater goods, and metal accessories and fasteners. | Downpipes / Sump | Inspection of product being installed / Sample | Approval of Sample + Shop Drawings
| Section 3.3 | Roofing | Specification | Details the requirements of the gutters and support system required for acceptance of falls. | Guttering | Inspection of product being installed / Testing | Photos / Test Report
| Section 3.5-3.6 | Roofing | Specification | Minimum thickness of the downpipes for downpipe to match sump. | Downpipes / Sump | Inspection of product being installed / Testing | Photos / Test Report
Manufacturers Specifcations | Colorbond Guttering and Downpipes | Roofing | Tech Data / Sample | Guidelines to installation and falls required to achieve desired roof drainage | Guttering | Inspection of product being installed / Sample, Review and approval of Tech Data to Consultants | Approval of Sample + Shop Drawings
Structural Steel
Project Requirement | - | Structural Steel | Certificate | Provide Construction Category Certification Certificate CC2 minimum | - | Witness | Certificate / SCA Webstie Lookup
NCC Volume 1:2019 | Part B1.4 (c) | Structural Steel | Requirement | Steel Structure Installation and Fabrication to comply with AS4100:2020 | - | Inspection | Certification of Installation
Australian Standard / New Zealand Standard 1554.1:2014 | Section 1.7.2 | Structural Steel | Requirement | Basic wledign requirements are outlined in this section for: - Qualified Welding Procedures - Suitably Qualified Welders - Welding Supervision - Within ppropriate requirements | Welding | Verification | Certification
| Section 4.12.2.1, 4.12.2.2 | Structural Steel | Qualifications | Details the requirements of qualification for the welders and evidence demonstrating ability ot gain qualification. | Welding | Verification | Certification
| Section 6.2.1 | Structural Steel | Inspection | Details the methods of inspection of completed welds and relevant types of imperfections that are granted to be suitable in the tables within this section. | Welding | Inspection | Photos / Test Report
| Section 7.2 | Structural Steel | Qualifications | States the requirements of certification of the inpsectors for qualification | Welding | Verification | Certification
| Section 7.3 | Structural Steel | Inspection | Details the methods that the qualified inspectors will be assessing for rejection of welds. | Welding | Inspection | Photos / Test Report
Australian Standard 4100:2020 | Section 1.1.1 | Structural Steel | Specification / Shop Drawings | This Standard sets out minimum requirements for the design, fabrication, erection, and modification of steelwork in structures in accordance with the limit states design method. The Drawings are designed in accordance with this Standard and are referenced within. | Structural Steel Framing to Support the Model | Hold Point on Shop Drawings | Reports / Drawings
| Section 2.2 | Structural Steel | Requirement | Test certificates required as evidence on conformance. | Structural Steel Framing to Support the Model | Witness | Test certificate / Reports
| Section 2.3.7 | Structural Steel | Requirement | Chem Anchors to be sent to the Engineer for approval for purpose and use. | Structural Steel Framing to Support the Model | Hold Point | Tech Data
| Section 2.4 | Structural Steel | Requirement | All steel castings shall be in accordance with AS 2074 and Project Drawings | Structural Steel Framing to Support the Model | Hold Point | Test Certificate / Design Report
| Section 3.1.2 | Structural Steel | Requirement | Design to comply with this section. Verify with engineer/designer. | Structural Steel Framing to Support the Model | Hold Point on Shop Drawings | Reports / Drawings
| Section 15.1 | Structural Steel | Assessment | Erection of steel - steel may be rejected depending on the quality of the steel or tensioning requirements | Structural Steel Framing to Support the Model | Inspection / Witness Reports | Test Certificate / Design Report / Photographs
| Section 17.1 | Structural Steel | Assessment | Defines the scope of proof tests on members and connections for where the steel must comply with the acceptance of strength and accessibility | Structural Steel Framing to Support the Model | Inspection / Witness Reports | Test Certificate / Design Report / Photographs
| Section 17.6 | Structural Steel | Assessment | Defines what is required in the test reports for satisfaction by the Australian Standard | Structural Steel Framing to Support the Model | Witness Reports | Test Certificates / Engineers Reports
Australian Standard 5131:2016 | Section 6.2 | Structural Steel | Requirement | Fabrication traceability relating to the test reports and certificates | Structural Steel Framing to Support the Model | Witness | Test certificate / Reports
| Section 6.3, 6.9 - 6.11 | Structural Steel | Requirement | Ensuring that steel is being handled / assembled and transported in the correct manner in accordance with the manufacturers specification | Structural Steel Framing to Support the Model | Facility Visit | Photographs
| Section 7.1.1, 7.4.2 | Structural Steel (Welding) | Requirement | Welds on site are to conform with AS/NZS 1554.1:2014 and quality confirmed in the Drawings / Specifications and be carried out under suitable management systems by a qualified contractor. | Structural Steel Framing to Support the Model | Inspection by Engineer | Certification of Welding by accredited Subcontractor
| Section 8.1, 8.2 & 8.3 | Structural Steel | Requirement | Bolts, Nuts and Washers used are to be in accordance with the project documentation and snug-fit without damage to threads | Structural Steel Framing to Support the Model | Inspection by Engineer | Tech Data / Test certificate / Reports
| Section 11.2.2 & 13.11 | Structural Steel | Requirement | Quality Management System to be compiled with the minimum stanadard as outlined. ITP for installation and erection of steel | Structural Steel Framing to Support the Model | Witness / Hold Point | ITP & QA / Reports
| Section 11.5, 11.6 | Structural Steel | Requirement | Erection methodology plan is required for the installation of the structural steel - taking into account the temporary supports and the like. | Structural Steel Framing to Support the Model | Hold Point | Methodology
| Section 13.2 & 13.3 | Structural Steel | Requirement | Regular inspections of the structural steel for any imperfections or non-compliance, work will be stopped if discovered. | Structural Steel Framing to Support the Model | Hold Point / Witness | ITP completion and Photos
| Section 13.6 | Structural Steel | Requirement | Inspeciton of Welding for compliance | Structural Steel Framing to Support the Model | Hold Point / Witness | ITP completion and Photos
| Section 13.7, 13.7.3-11 | Structural Steel | Requirement | Inspection of Mechanical Fastners | Structural Steel Framing to Support the Model | Hold Point / Witness | ITP completion and Photos
| Section 13.8 | Structural Steel | Requirement | Inspection of Surface Treatment | Structural Steel Framing to Support the Model | Hold Point / Witness | ITP completion and Photos
Roof mesh
NCC Volume 1 | Part B1.4, (j - iii, iv) | Roofing | Requirement | Safety mesh installed on site in accordance with AS/NZS1562.3 with technical data approved by consultants or specified in the specifications provided. | Roofing Material | Certification from installer | Certification of Installation
Australian Standard 4389:2015 | Section 5 | Roofing | Specification / Shop Drawings / Sample | Roof Safety Mesh shall cover the entire roof area for fall protection when working at heights in domestic, commercial and industrial building applications that use metal or timber purlins, or a tested supporting member. | Roof Material | Hold Point on Shop Drawings | Approval of Sample + Shop Drawings
| Sections 7.1.1 & 7.1.2 | Roofing | Requirement | Minimum requirements for the Safety Mesh / Wire for acceptance and manufacture. | Roof Material | Certification from Supplier and Installer | Tech Data / Certification of Installation
| Section 9.2 | Roofing | Requirement Installation | Installation requirement and layering when on conventional metal roofing with insulation and sarking, this is shown on consultants section drawings and shop drawings | Roof Material | Hold Point on Shop Drawings | Approval of Sample + Shop Drawings
| Section 9.3 | Roofing | Requirement | Minimum spacings and Lapping for the specified material | Roof Material | Inspection | Certification of Installation / Photographs
Australian Standard / New Zealand Standard 4534:2006 | Section 6 | Roofing | Certificate | Acceptance that Zinc and zinc/aluminium-alloy coatings on steel wire are free from defects and match Tech Data | Roof Material | Hold Point / Witness / Inspection | Reports / Tech Data
Manufacturers Specifcations | Safety mesh | Roofing | Tech Data / Sample | Guidelines to installation and lapping requirements as per Australian Standard 4389:2015. | Roof Material | Inspection of product being installed / Sample, Review and approvval of Tech Data to Consultants | Approval of Sample + Shop Drawings
Sarking / Insulation
NCC Volume 1 | Part F1.6 | Roofing | Requirement | Sarking used for weatherproofing of roof must comply with Installation in AS 4200.2. | Sarking | Certification from Installer | Certification of Installation
| Part J0.4 (a),(b) | Roofing | Requirement | The purlins and roof sheeting will be signed off by a qualified installer that the roof does contain a thermal break | Insulation and Fixing method of Sheeting | Certification from Installer | Certification of Installation
Australian Standard 1530.1:1994 | Section 2 - Test for flammability of materials | Roofing | Certificate | Test results from famibility fire tests on building materials, components and structures to be referencd in the Technical Data submitted to the engineer for approval. | Insulation | Technical Data / Reports | Technical Data / Reports
Australian Standard 1530.1:1994 | Section 3 - Calculation and Reporting of Results | Roofing | Certificate | Methods for fire tests on building materials and structures - Test for early fire hazard properties of materials to be included in Technical Data | Insulation | Technical Data / Reports | Technical Data / Reports
Australian Standard 4200.2:2017 | Section 3.2 | Roofing | Requirement | Installation Requirement for cutting, exposure and repairing damage or rejection of sarking when delievered / installed. | Sarking | Certification from Supplier / Installer | Sign Off / Photos
| Section 3.3 | Roofing | Requirement | Details minimum jointing requirements and cutting. | Sarking | Certification from Supplier / Installer | Sign Off / Photos
| Section 3.4 | Roofing | Requirement | Installation of membrance under sheet roofing being parallel to fascia and direction of lapping | Sarking | Certification from Supplier / Installer | Sign Off / Photos
Australian Standard 4859.1:2018 | Section 6.2 | Roofing | Certificate | This Standard provides the methods of test for the materials that are used and should be referenced in the test reports submitted as part of the technical data. | Roof | Certification from Supplier | Test Report
| Section 9.2 | Roofing | Certificate | Details the properties of reflective material bonded directly to a substrate | Insulation / Sarking | Certification from Supplier | Test Report
Manufacturers Specifications | Pliable waterproof membrane | Roofing | Type / Sample | Product to be installed within the requirements of the specification to comply with tested properties that will be referenced in the document. | Sarking | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
| Low Density Polyester Blanket - Bradford Equivalent | Roofing | Type / Sample | Product to be installed within the requirements of the specification to comply with tested properties that will be referenced in the document. | Insulation Laying and Placement | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
Roofing
NCC Volume 1 | Part C1.10 | Roofing | Requirement | Fire Hazard properties must be tested for product conformity of materials | Guttering / Roof Panels / Roof Sheeting | Technical Data / Reports | Technical Data / Reports
| Part F1 - FP1.4 | Roofing | Requirement | The roof will prevent moisture entering the covered space through sarking and seals around roofing penetrations for water tightness. Test Results will be provided of flashings and sealants. | Flashings to roof penetrations / Sealants | Inspection of product being installed with guidelies/ Sample | Certification of Installation
| Part F1.5 (d) | Roofing | Requirement | The roof must be covered with metal sheet roofing complying with AS 1562.1. | Roofing Material | Certification from installer | Certification of Installation
Australian Standard 1530.1:1994 | Section 1 - Combustibility Test for Building Materials | Roofing | Certificate | Test results from combustibility fire tests on building materials, components and structures to be referencd in the Technical Data submitted to the engineer for approval. | Guttering / Roof Panels / Roof Sheeting | Technical Data / Reports | Technical Data / Reports
Australian Standard 1562.1:1992 | Section 4.1 | Roofing | Requirement | Installation of the Roof Sheeting to be within the manufacturers guidelines | Roof Cladding | Manufacturer Installation Certificate by Certified Installer | Manufacturer Installation Certificate by Certified Installer
| Section 4.2-4.3 | Roofing | Requirement | Supports to be provided for hips and valleys as well as within mnufacturers guidelines | Roof Supports | Manufacturer Installation Certificate by Certified Installer / Photos | Manufacturer Installation Certificate by Certified Installer / Photos
| Section 4.4 | Roofing | Requirement | Installation of roof sheeting within the tolerances detailed in this section for overhangs and bird / vermin entry | Roof Cladding | Manufacturer Installation Certificate by Certified Installer / Hold Point | Manufacturer Installation Certificate by Certified Installer / Hold Point
| Section 4.5 - 4.7 | Roofing | Requirement | Details the requirements for Fixing and Fastening of the roof sheeting and the appropriate methods that are to be used for the cutting of edges of sheets and gutters. | Roof Cladding / Gutters | Certification from Installer / Photos | Certification from Installer / Photos
| Section 4.8 | Roofing | Requirement | Flashings are required to prevent the ingress of water into the water space - this standard details the requirements and standards for installation of compliant flashings around penetrations | Flashings | Certification from Installer / Photos | Certification from Installer / Photos
| Section 4.9 | Roofing | Requirement | Roofing material is to be protected from damage during construction including the protection from swarf and the like when grinding - this will be defected and have the onset of oxidisation on the metal. | All Roofing area | Certification from Installer / Photos | Certification from Installer / Photos
| Section 5.1 | Roofing | Certificate / Requirement | Compliance for testing of the roofing materials in compliance with AS 4040, to be referenced technical data provided to engineer / architect for approval | Roofing Material | Technical Data / Certification from Supplier | Technical Data / Certification from Supplier
Australian Standard 4284:2008 | Section 10.1-10.2 | Roofing | Certificate / Requirement | Testing of building facades This Standard is to be referenced in the techinical data when submitted for approval which sets out a method for determining the performance of a representative building facade under simulated conditions of loading. | Roof | Technical Data / Certification from Supplier | Technical Data / Certification from Supplier / Reports
Australian Standard / New Zealand Standard 4654.2:2012 | Section 2.8.2.3 | Roofing | Requirement | Shows the minimum downturn for flashings externally for gutter termination | Vertical Flashing to Gutter | Shop Drawings / Hold Point | Approval of Sample + Shop Drawings / Photos
| Section 2.8.4 | Roofing | Requirement | Details the requirement of Penetration Waterproofing | Penetration | Shop Drawings / Hold Point | Approval of Sample + Shop Drawings / Photos
| Section 2.16 | Roofing | Requirment | Acceptance testing methods for waterproofing elements for water-tightness | Waterproofing around penetrations | Test Reports / Videos | Test Reports / Videos
Australian Standard 4859.1:2018 | Section 6.2 | Roofing | Certificate | This Standard provides the methods of test for the materials that are used and should be referenced in the test reports submitted as part of the technical data. | Roof | Certification from Supplier | Test Report
Manufacturers Specifications | Bondor - SolarSpan | Roofing | Type / Sample | Guideline provided by the manufacturer of the product. Product to be installed within the requirements of the manual to comply with tested properties AS1530.3 Test for flammability from NCC C1.10. | Roof Sheeting with Expanded polystyrene Core and continuous steel ceiling finish. | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
| Kingklip | Roofing | Type / Sample | Guideline provided by the manufacturer of the product. Product to be installed within the requirements of the manual to comply with tested properties | Ensuring KlipLok brackets are installed ontop of the spacers on the purlins as per manufacturers specifications | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
| Lysaght | Structural Steel | Type / Sample | Guideline provided by the manufacturer of the product. Product to be installed within the requirements of the manual to comply with tested properties | Spacings as per manufacturers specifications | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
Roof Safety System
Australian Standard 1657:2018 | Section 2.2 | Roofing Safety System: Walkway | Requirement | Details the requirement of installation of walkway onto roofing material shall not exceed an angle of >20 deg in the direction of travel | Aluminium Walkway | Hold Point on Shop Drawings / Tech Data | Approval of Shop Drawings
| Section 8.1 | Roofing Safety System: Walkway | Requirement | Labelling of the Installation shall require date, name of certifier, company etc. | Aluminium Walkway | Inspection of the installed equipment | Photo Verification / Correct sign off
| Appendix B | Roofing Safety System: Walkway | Requirement / Type / Sample | Details testing methods of the roof walkway systems | Aluminium Walkway | Hold Point on Shop Drawings / Sample | Approval of Sample + Shop Drawings
| Appendix E | Roofing Safety System: Walkway | Requirement / Type / Sample | Testing of the assemblies or components shall require information outlined in this section referencing Appendix B for testing methods | Aluminium Walkway | Hold Point on Shop Drawings / Sample | Approval of Sample + Shop Drawings
Manufacturers Specifications | Aluminium Walkway Sample | Roofing Safety System: Walkway | Type / Sample | Guideline provided by the manufacturer of the product. Product to be installed within the requirements of the manual to comply with tested properties | Aluminium Walkway | Inspection of product being installed with guidelies/ Sample | Approval of Sample + Shop Drawings
Concrete (Slab)
Australian Standard 1379:2007 | Section 3.5 | Concrete Supplier | Mix Design Certification | Concrete supplied to site is to conform with the project requirements and the Standard for mixture and additives | Concrete Supply | Technical Data / Certification from Supplier | Compliance with Mix Design
| Section 4.2 & 4.4 | Concrete Supplier | Certification | Concrete supplied to site is within the maximum time frame allowed for delivery for temperature. | Concrete Supply | Docket Review | Delivery Docket / Certificate of Mix Design
| Section 5.1.1, 5.2 | Concrete Supplier | Type / Sample | Testing requirements for the slump and mix design | Concrete Supply | Certification from Supplier | Test Report
| Section 5.3 & 5.7 | Concrete Supplier | Certification | Strength Testing 7 & 28 Days for the Concrete | Concrete Supply | Certification from Supplier | Test Report
Australian Standard 3600:2018 | Section 17.1.7.1 | Concretor | Type / Sample | Placement of Concrete - concrete may be rejected depending on the quality of the placement requirements | Concrete Slab | Inspection / Witness Reports | Test Certificate / Design Report / Photographs
| Section 17.2.3 | Concretor / Reinforcement | Requirement | Details the bending / re-bending of reinforcement and the standards to avoid damage to the bar | Reinforcement | Installation certification | Certificate of compliance - Reinforcement
| Section 17.2.4 | Concretor / Reinforcement | Requirement | Refers to the acceptable condition of the re-bar prior to installation | Reinforcement | Installation certification | Certificate of compliance - Reinforcement / Photos
| Section 17.2.5 | Concretor / Reinforcement | Requirement | Details the requirement of fixing and positions of tendons and tolerances within the tables in this section | Reinforcement | Installation certification | Certificate of compliance - Reinforcement / Photos
| Section 17.4 | Concretor / Structural Steel | Requirement | Construction Requirements for Cast In Plates prior to Slab Pour | Cast In Plates | Inspection / Witness | Photographs
| Section 17.6.2.1, 17.6.2.3 | Formwork | Requirement | Formwork shall be installed, signed off by consultant and stripped in compliance with the standard, otherwise will be dismantled and rejected. | Formwork | Inspection / Witness Certification | Certificate of compliance - Formwork
| Section 19.3.3 | Structural Steel | Requirement | Cast-in elements shall be installed in accordance with this specification | Cast In Plates | Inspection / Witness Reports | Test Certificate / Design Report / Photographs
Australian Standard / New Zealand Standard 4671:2019 | Section 9 | Reinforcement | Requirement | Details the requirements for product confirmity | Reinforcement | - | -
| Section 10.1, 10.4 | Reinforcement | Requirement / Certification | Reinforcing steels require certificates with a marking system that can be identified. | Reinforcement | Inspection / Certfication / Reports | Test Certificate / Design Report / Photographs
| Section 10.2-10.3 | Reinforcement | Requirement | Identification of the Steel producer and labelling for supply | Reinforcement | Inspection of identification marks | Visual / Photographs